## Sheet1
| PROJECT NAME | PROJECT DURATION | PROJECT START DATE | PROJECT END DATE
| bank Management System | 9 days | July 02, 2021 | July 10, 2021
TASK ID | TASK DESCRIPTION | TASK DURATION | START DATE | END DATE | July 02, 2021 | July 03, 2021 | July 04, 2021 | July 05, 2021 | July 06, 2021 | July 07, 2021 | July 08, 2021 | July 09, 2021 | July 10, 2021
1 | Creating Template | 1 | July 02, 2021 | July 03, 2021
2 | Install Dependencies and extension and Creating Repo on github | 1 | July 03, 2021 | July 04, 2021
3 | Implementation Phase 1 - working with Logic of System | 1 | July 04, 2021 | July 05, 2021
4 | Implementation Phase 2 - working with Source Code | 2 | July 04, 2021 | July 06, 2021
5 | Creating Github Action | 1 | July 06, 2021 | July 07, 2021
6 | Working on github Like raising Issues | 1 | July 07, 2021 | July 08, 2021
7 | Working with testing and report | 1 | July 08, 2021 | July 09, 2021
8 | TESTING AND FINAL TOUCH | 2 | July 08, 2021 | July 10, 2021